## Backlog
ID | Phase | Priority | Epic | Task | Acceptance Criteria | Owner(AI) | Est(days) | Dependencies | Notes
T-001 | P0 | Must | Foundation | Repo init (Next.js TS, lint, prettier) | CI build/test passes | Copilot | 0.5
T-002 | P0 | Must | Foundation | Supabase schema apply (v3) | All tables exist; local env connects | Copilot | 0.5 | T-001 | Use 07_DB_Schema_v3.sql
T-003 | P0 | Must | YouTube | parseYouTubeVideoId(url) | Unit tests cover watch/shorts/youtu.be/embed; invalid->null | Copilot | 0.5 | T-001
T-004 | P0 | Must | YouTube | YouTube Data API client (videos.list) | Handles quota/404; returns snippet/contentDetails | Copilot | 0.5 | T-003 | Mock tests
T-005 | P0 | Must | Extraction | description cleaner + chapter extractor | Unit tests for URL removal + timestamps | Copilot | 1 | T-004
T-006 | P0 | Must | Extraction | LLM wrapper (Prompt A) + zod validation | Retries invalid JSON; logs extraction_runs | Copilot | 1 | T-005
T-007 | P0 | Must | API | POST /api/recipes/import (stores card) | Creates video_sources, recipes, ingredients, steps | Copilot | 1.5 | T-002,T-004,T-006
T-008 | P0 | Must | UI | Home screen (paste URL + recent list) | Paste/import works; shows recent cards | Copilot | 1 | T-007
T-009 | P0 | Must | UI | RecipeDetail (ingredients/steps + nutrition box placeholder) | Shows card; confidence badge; video link | Copilot | 1 | T-007
T-010 | P0 | Must | UI | CookMode (step-by-step + timer) | Mobile-friendly; checklist works; timer works | Copilot | 2 | T-009
T-011 | P0 | Must | Nutrition | Ingest food DB (MEXT) | food_items and nutrients populated; search works | Copilot | 1.5 | T-002 | Use 16_Runbook
T-012 | P0 | Must | Nutrition | matchFoodItem + parseQuantity + computeNutrition | Returns totals+confidence+coverage+unresolved | Copilot | 2 | T-011 | Unit tests
T-013 | P0 | Must | API | POST /api/recipes/{id}/nutrition | Computes and caches nutrition; returns unresolved list | Copilot | 1 | T-012
T-014 | P0 | Must | UI | NutritionFix screen (quick edits) | Candidate select + grams input; saves overrides | Copilot | 2 | T-013
T-015 | P0 | Must | API | PATCH /api/ingredients/{ingredient_id}/match | Stores manual match+grams; triggers recompute | Copilot | 1 | T-014
T-016 | P0 | Should | Growth | Share slug + public page | Share page includes embed+credit; slug rotation | Copilot | 1.5 | T-009
T-017 | P0 | Must | Testing | Playwright E2E 3 scenarios | E2E passes in CI | Copilot | 2 | T-008,T-010,T-014
T-018 | P1 | Should | Quality | Channel-specific parser (e.g., Ryuji) | Improves extraction on 10 sample URLs | Copilot | 1.5 | T-005
T-019 | P1 | Could | Search | Tags + nutrition filter | Filter by protein density etc | Copilot | 2 | T-012
T-020 | P0 | Must | Compliance | Terms/Privacy pages + disclaimers | YouTube links + nutrition disclaimers present | Copilot | 1 | T-008